## Sheet1
Tasks | Create Project Objective
Recruit Team Memebers
Research & Purchase Robotic Systems
Design & Build Sensor Test Platform
Test Sonar Sensor for Accuracy
Design & Build Robot Chasis
Develop Program to Control Robot Remotely
Develop Program to Integrate Motors with Sensor Readings
Reasarch MCL Methods
Develop Program to Map Environment and Robot
Design & Build Test Environment
Add MCL to Program
Add A* to Program
Troubleshoot Program
Optimize Program
Provide Full Demonstration
Report
|  | 2011-01-17 | 2011-01-24 | 2011-01-31 | 2011-02-07 | 2011-02-14 | 2011-02-21 | 2011-02-28 | 2011-03-07 | 2011-03-14 | 2011-03-21 | 2011-03-28 | 2011-04-04 | 2011-04-11 | 2011-04-18 | 2011-04-25 | 2011-05-02 | 2011-05-09 | 2011-05-16 | 2011-05-23 | 2011-05-30 | 2011-06-06